## Task Tracker
ID | Priority | Stage | Title | Issue | Claude Fix Prompt | Acceptance Criteria | Status
P1-07 | P1 | Product Experience | Retention Intelligence Hero Experience | Make the AI assistant unmistakably the flagship product, not a chatbot attached to a dashboard. | Reframe the experience around What is happening → Who needs attention → Why → What should I do → Take action. Improve hero, context, suggested questions, evidence/action hierarchy and paths to Customer 360/Priority Customers. Preserve deterministic grounding. No LangChain, vector DB, new ML, or analytical/model/output changes. Validate browser + tests. | Flagship identity is obvious; manager workflow is understandable; evidence/actions distinct; grounding intact; no notebooks/models/outputs/src changes; tests and browser flow pass. | REVIEW
P1-08 | P1 | Product Experience | Manager Command Workflow | The six pages can still feel like separate screens instead of one retention operation workflow. | Create a coherent Overview → Priority Customers → Customer 360 → Retention Intelligence journey. Preserve deep links and context, prevent stale session state, reuse existing tools/data, and avoid duplicated analytical logic. Validate fresh navigation, handoffs and refresh. | Portfolio signal leads to cohort; cohort leads to customer; customer leads to assistant; context survives handoffs; no stale state; browser + full tests pass. | REVIEW
P1-09 | P1 | AI Product | Assistant Identity & Personality | The AI capability risks looking generic rather than deliberately designed. | Give the assistant a distinctive professional identity: name treatment, role, voice, context/status cues and restrained visual treatment. Do not imply autonomous actions it cannot perform. Preserve Model Risk Score, Estimated Churn Probability, HRR and High-Risk Historical Revenue Exposure terminology. No emoji, cartoon avatar, gradients or fake activity. | Consistent identity; accurate capability claims; professional visual treatment; grounded terminology preserved; tests/browser pass. | REVIEW
P1-10 | P1 | UX / Information Design | Numbers-to-Decisions Pass | There is still a risk of numbers overload, making action priorities hard to see. | Audit all six pages. For every major metric ask whether it answers a manager question. Prefer signal → interpretation → implication/action. Keep necessary evidence accessible but reduce equal-weight KPI/card density. Use existing values only; no calculation changes. | Each page has one obvious primary question; supporting metrics have lower visual weight; evidence remains accessible; density improves; no analytical changes; tests/browser pass. | REVIEW
P1-11 | P1 | UX / AI | Evidence → Recommendation Presentation | The strongest differentiator—grounded decision support—should be visually obvious. | Present responses as Finding → Evidence → Why it matters → Recommended action → Confidence/limitations → Next step where applicable. Use existing structured tool results and deterministic answer path. Do not re-query, invent facts, claim causality, or call Model Risk Score a probability. Keep customer/cohort links working. | Evidence and action are distinct; uncertainty is honest; terminology guardrails remain; next-step links work; representative edge cases pass. | TODO
P1-12 | P1 | AI Product | LLM Tool-Use Production Hardening | The optional Anthropic path has not had a real API completion test in the current environment. | Harden missing key, timeout, malformed tool call, invalid tool, malformed response, partial failure and repeated-call cases. Keep allow-list and bounded loop. If an API key exists, run a controlled live smoke test; otherwise never fabricate one and expand contract tests. Deterministic fallback must always work. No analytical changes/dependencies unless strictly necessary. | All failure modes safely fall back; no arbitrary execution; deterministic path works without key; live test reported only if actually performed; tests pass. | TODO
P1-13 | P1 | Demo / Presentation | Five-Minute Demo Flow | A technically strong product can underperform if its value is not obvious quickly. | Optimize for a fresh evaluator: business problem → platform value → Retention Intelligence → real portfolio question → cohort/customer → evidence → recommendation → reusable architecture. Make only UI/navigation/context changes needed. No invented claims; no hidden setup. | Purpose understood within ~60 seconds; hero workflow reached quickly; real customer/cohort demo works from fresh state; claims grounded; tests/browser pass. | TODO
P1-14 | P1 | Reusable Platform | KKBox-to-Reusable Architecture Story | The solution needs a defensible explanation of what is KKBox-specific versus reusable. | Audit the pipeline and document domain-specific inputs versus reusable retention decision-support architecture. Explain KKBox as validation use case, without claiming validated performance elsewhere. Only add genuinely supported configuration/abstraction; do not change model outputs. | Product/docs clearly separate evidence from general architecture; no unsupported claims; evaluator questions about dataset choice are answerable; tests pass. | TODO
P1-15 | P1 | Final QA | Integrated Product QA | Sequential feature work creates cross-feature regression risk. | Perform a no-code-first audit, then full tests, syntax/import checks, fresh server, all six pages, manager workflow, customer/segment switching, unknown/missing-data/special-character IDs, no-key behavior, deep links, currency/terminology and desktop overflow. Fix only genuine P1 regressions and add regression tests where practical. Do not start P2. | Full suite and browser flows pass; edge cases pass; currency/terminology consistent; notebooks/models/outputs/src untouched; remaining limitations documented; no P2 begins. | TODO
P2-16 | P2 | Optional Polish | Final Visual Polish | Only after functional readiness, small visual inconsistencies may remain. | After P1-15, fix only concrete spacing, typography, alignment, component-reuse and supported responsive inconsistencies. No new features, gimmicks, emoji, gradients or analytical changes. Re-run demo path and full tests. | Concrete visual issues fixed only; no feature creep; demo unchanged; tests/browser pass; analytical files untouched. | TODO

## Execution Roadmap
Ticket | Goal
P1-07 | Flagship experience
P1-08 | Manager workflow
P1-09 | Assistant identity
P1-10 | Information hierarchy
P1-11 | Evidence-to-action
P1-12 | LLM hardening
P1-13 | Five-minute demo
P1-14 | Reusable architecture story
P1-15 | Integrated freeze QA
P2-16 | Optional final polish

## How to Use
Rule | Instruction
Status | TODO → IN PROGRESS → REVIEW → DONE. Update only the active ticket.
Execution | One ticket at a time. Validate before starting the next.
Validation | Create a validation report in test_cases/ for every implementation ticket.
Scope | Do not modify notebooks, models, outputs, src/ or analytical calculations unless explicitly required.
Grounding | Never invent customer facts, metrics, probabilities, recommendations or business outcomes.
LLM boundary | LLM narrates grounded tool results; deterministic tools remain the source of truth and allow-list enforcement.
Product goal | Optimize for manager usefulness and evaluator comprehension, not feature count.
Stop condition | If a change threatens analytical correctness or requires unnecessary dependencies, stop and report the risk.